## Sheet1
ID | Area | Feature | Sub-feature | Description | Priority | Status | Owner | Start | Due | Acceptance Criteria | Source
A-01 | A | Sign up | Terms / Privacy consent | Agreement to Terms of Service and Privacy Policy during sign up. | Must | Not started |  |  |  | Cannot sign up without required consent. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
A-02 | A | Login | ID / Password / Auto login | Include options for saving ID and enabling auto login. | Must | Not started |  |  |  | Issue and maintain session/token. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
A-03 | A | SNS Login | Facebook / Google / Kakao / Naver | SNS OAuth-integrated login. | Should | Not started |  |  |  | After OAuth, link account and handle new-member creation. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
A-04 | A | Find ID info | Mobile real-name verification | Find ID based on real-name verification. | Must | Not started |  |  |  | If mobile identity verification succeeds, recover the ID. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
A-05 | A | Find members | Conditional search | Find members by conditions such as birth year. | Could | Not started |  |  |  | Return results when conditions are entered. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
A-06 | A | Real-name verification guide | Mobile identity verification | Section describing the real-name verification process/guide. | Should | Not started |  |  |  | Invoke the linked module and receive the result. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
A-07 | A | My Page | Reservations / Inquiries / Favorites | Manage reservation history, inquiry history, and favorites in My Page. | Should | Not started |  |  |  | Each list supports view/detail/cancel/delete actions. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
A-08 | A | Member info | Profile / Change password | Edit member profile and change password in My Page. | Could | Not started |  |  |  | Comply with password policy and log history. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
B-01 | B | Enter booking | Book button | Enter booking flow from list/detail by clicking book. | Must | Not started |  |  |  | Pass selected room/date. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
B-02 | B | Payment methods | Naver Pay / Kakao Pay / Credit card (interest‑free) | Guide payment methods and integrate payment. | Must | Not started |  |  |  | Handle success/failure callbacks. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
B-03 | B | Bank transfer | SMS guidance | Send SMS after confirming bank transfer. | Should | Not started |  |  |  | Trigger SMS upon deposit confirmation. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
B-04 | B | Refund policy | Penalty/Refund ratio | Calculate/show refunds per policy. | Must | Not started |  |  |  | On cancellation, compute amount per policy. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
B-05 | B | Check reservation | Lookup / Cancel | Global entry to lookup/cancel using reservation no. and auth info. | Must | Not started |  |  |  | After identity verification, show details/cancel. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
B-06 | B | Booker info | Real name / Phone / Requests | Enter booker’s real name, mobile no., email, and requests. | Must | Not started |  |  |  | Validate required fields and confirm ToS consent. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
B-07 | B | Points | Use / Earn | Use and accrue points at payment stage. | Should | Not started |  |  |  | Deduct/accrue correctly and reflect on receipt. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
B-08 | B | Booking form fields | Dates / People / Duration / Rooms / Options | Choose check‑in/out, people, nights, number of rooms, options. | Must | Not started |  |  |  | Validate and compute total price. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
B-09 | B | Consent to terms | Cancellation / Refund / Privacy | Terms consent checkboxes before booking. | Must | Not started |  |  |  | If not agreed, block payment and show notice. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
B-10 | B | Receipt/Notifications | Email / SMS | Send receipt/confirmation via email and SMS on completion. | Should | Not started |  |  |  | Send using templates and log dispatch. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
B-11 | B | Completion screen | Reservation number | Show reservation number/summary on completion page. | Must | Not started |  |  |  | Allow copy/share of reservation code. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
B-12 | B | Lookup input fields | Reservation no. / Email / Mobile no. | Fields for reservation lookup form. | Must | Not started |  |  |  | Allow lookup with at least 2 of the 3 combinations. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
B-13 | B | Cancel reservation | Reason entry / Policy notice | Enter reason and re‑notify policy upon cancellation. | Should | Not started |  |  |  | Show cancellation done and refund schedule. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
C-01 | C | Contact Us | Inquiry form | Name/phone/mobile/email/photo/inquiry items + captcha + notice about saving to My Page. | Must | Not started |  |  |  | Validate required fields, captcha, save, and notify. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
C-02 | C | Customer Center hub | Recent posts / Sections | Hub for posts such as Notices and Vendor Inquiry. | Should | Not started |  |  |  | Display categories and recent posts. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
C-03 | C | FAQ | Board | List and search Frequently Asked Questions. | Should | Not started |  |  |  | Categories, search, and paging work. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
C-04 | C | Merchant onboarding inquiry | Board | Board to receive merchant/partner inquiries. | Should | Not started |  |  |  | Create post/list/detail/comment. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
C-05 | C | Board – common | List / Detail / Comments / DM / Recommend / Views | Show title/author/date/recommend-count/view-count/comments[n], pagination, send DM. | Should | Not started |  |  |  | CRUD, permissions, anti-spam, and paging work. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
C-06 | C | User guide | Board | User guide documents/board. | Should | Not started |  |  |  | List/detail/search/attachments available. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
C-07 | C | Q&A | Board | Q&A board. | Should | Not started |  |  |  | Register questions, answers, and show solved status. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
C-08 | C | Ads inquiry | Form / Board | Accept advertising inquiries. | Could | Not started |  |  |  | Form submission, admin notification, assign counselor. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
C-09 | C | Board attachments | File / Image upload | Attach files/images to board posts. | Should | Not started |  |  |  | Enforce extension/size limits and virus scan. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
F-01 | F | Policy pages | Terms of Use / Privacy | Expose full policy pages. | Must | Not started |  |  |  | Provide version, revision date, and anchors. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
F-02 | F | Company info | Business license / E-commerce registration / Contacts | Expose legally required notice information. | Must | Not started |  |  |  | Keep info up to date; contact click works. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
F-03 | F | Notices | Board | Manage/expose the notices board. | Should | Not started |  |  |  | List/detail/search available. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
G-01 | G | Top navigation | Primary categories | Provide and navigate menus for Regional Pensions, Vacant Room Search, Spa Pensions, Workshop/Group Pensions, Pool Pensions, Glamping & Caravan. | Must | Not started |  |  |  | When each tab is clicked, route to the corresponding category page. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
G-02 | G | Global entry | Check reservation | Provide entry to 'Check Reservation' from the header or top utility area. | Must | Not started |  |  |  | On click, navigate to the reservation inquiry screen. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
G-03 | G | Utility links | Sign up / Vendor inquiry / Customer center | Provide utility links at the top. | Should | Not started |  |  |  | Each link routes correctly. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
G-04 | G | Weather badge | City selection + temperature/icon | Expose nationwide city selection and current weather/temperature badge. | Should | Not started |  |  |  | When a city is selected, the badge updates to that city’s info. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
G-05 | G | Recently viewed | Widget | Show recently viewed pensions with an empty state 'No pensions viewed today.' | Must | Not started |  |  |  | Update/show the list after visiting an accommodation detail page. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
G-06 | G | Favorites | Add to favorites | Add/remove favorites on accommodation cards/details. | Should | Not started |  |  |  | Store locally for guests; sync to server for members. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
G-07 | G | Footer | Policies / Company info | Show About, Ad Inquiry, Privacy Policy, Terms, Notices, Support, RSS, and business/license/contact info. | Must | Not started |  |  |  | All policy pages are accessible. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
G-08 | G | Mobile version link | Mobile link | Provide a mobile version link in the top utility area. | Could | Not started |  |  |  | On click, go to the mobile page. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
G-09 | G | RSS | RSS link | Expose the RSS link in the footer. | Could | Not started |  |  |  | RSS link responds correctly. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
L-01 | L | Accommodation card | Key info | Show region/summary/min price (weekday/weekend) on cards. | Must | Not started |  |  |  | Clicking a card opens the detail page. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
L-02 | L | List actions | Instant booking / Inquire / View details | Provide action buttons on card/list. | Must | Not started |  |  |  | Each button routes and works properly. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
L-03 | L | Badges | Recommended / Popular / Premium / New | Show badges on some cards. | Could | Not started |  |  |  | Show a badge when conditions match. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
L-04 | L | Empty state | No search results | Show empty-state message when no results. | Must | Not started |  |  |  | Refresh results when conditions change. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
P-01 | P | Top gallery | Image slider | Top image gallery/slider on accommodation detail. | Must | Not started |  |  |  | Support swipe/thumbnails. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
P-02 | P | Share/Print/Report | Twitter / Print / Report | Share (Twitter), print, and report buttons at the top of detail. | Should | Not started |  |  |  | Each button functions with dialog/routing. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
P-03 | P | Basic info | Consultation / Payment guide / Events | Show accommodation name, CS number/hours, payment guide (Naver Pay/Kakao Pay/interest‑free cards), event discounts, etc. | Must | Not started |  |  |  | Standardize info section and show guide text. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
P-04 | P | Usage info | Check‑in/out, Parking/Pets/Pick‑up | Show check‑in/out times; parking, pet‑friendly, and pick‑up info. | Must | Not started |  |  |  | Display policies/guides. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
P-05 | P | Address/Map | Map section | Show address and render map. | Must | Not started |  |  |  | Coordinates and address must match. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
P-06 | P | Rooms & Rates | Availability table | Room name, min/max occupancy, area, weekday/holiday rates (off/peak), book button. | Must | Not started |  |  |  | Reflect selected date/options and enter booking. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
P-07 | P | Amenities/Themes | List | List accommodation amenities/themes. | Should | Not started |  |  |  | Dynamically display per accommodation data. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
P-08 | P | Guides/Policies | Cautions / Refund policy table | Basic notes/cautions; refund policy (table). | Must | Not started |  |  |  | Refund policy is calculated/displayed per spec. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
P-09 | P | Reviews | User ratings / Opinions | Expose reviews/ratings area. | Should | Not started |  |  |  | Review list, rating aggregation, paging. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
P-10 | P | Recommendations | Nearby accommodations | List recommended places nearby. | Could | Not started |  |  |  | Show recommendations based on current detail location. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
P-11 | P | Booking calendar | Availability calendar | Calendar UI showing room‑level availability. | Must | Not started |  |  |  | Month switching, blackout dates, and selection linkage. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
R-01 | R | Ranking/Stats | Rank by category | Expose rankings per category. | Could | Not started |  |  |  | Document ranking criteria and keep sorting consistent. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
R-02 | R | Compare selection | Company comparison | Feature to select multiple companies and compare. | Could | Not started |  |  |  | Generate a comparison table for selected items. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
R-03 | R | View stats | Views / Scraps / Inquiries / Ratings count | Display statistical indicators. | Could | Not started |  |  |  | Collect, aggregate, and apply caching. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
S-01 | S | Vacant room main | HOME > Vacant room | Landing screen and navigation indicator for vacant-room search. | Must | Not started |  |  |  | Breadcrumbs/header title visible. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
S-02 | S | Regional search | Region grid + counts | Region grid with result counts per region. | Must | Not started |  |  |  | Route/filter results to the selected region. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
S-03 | S | Map exploration | Droplet markers | Toggle/Show map per the note 'When checked, search with the droplet map.' | Should | Not started |  |  |  | Markers display and sync with list when toggled. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
S-04 | S | List sorting | Newest/Title/Views | Sorting for search results. | Must | Not started |  |  |  | Changing sort reorders results. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
S-05 | S | Pagination | Numbered pages | Navigate between result pages. | Must | Not started |  |  |  | Page change syncs results and URL. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
S-06 | S | Category lists | Pool villa / Spa / Group / Glamping etc. | Provide category card lists (weekday/weekend lowest price, badges). | Must | Not started |  |  |  | Category tab/page loads and shows results. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
S-07 | S | Unified search | ALL SEARCH | Global search segmented by sections (reservations/community, etc.). | Should | Not started |  |  |  | Show results per section when a query is entered. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
S-08 | S | Theme/Amenities options | Select up to 3 | Select options like beach/valley/Wi‑Fi/pool/parking/pet‑friendly/spa, etc. | Should | Not started |  |  |  | Limit to 3 selections and reflect in results. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
S-09 | S | Header search bar | Enter global search | Header search box that enters unified search. | Should | Not started |  |  |  | Entering a query goes to ALL SEARCH. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
S-10 | S | Support banner | Main number / Hours | Show the main customer support phone number and service hours on unified search/other pages. | Should | Not started |  |  |  | Tap-to-call; show service hours. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
U-01 | U | Print | Print page | Print the detail page. | Could | Not started |  |  |  | Apply print styles. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
U-02 | U | Share | Share on Twitter | Share the detail page to Twitter. | Could | Not started |  |  |  | Verify share link and OG meta. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C
U-03 | U | Report | Report content | Accept reports for the detail content. | Could | Not started |  |  |  | Enter reason, submit, and notify admin. | https://pensiondanawa.com/html_file.php?file=all_emptyroom.html&file2=default_emptyroom.html&search_theme=%EC%98%A8%EC%B2%9C